## Team
Initials | First | Last | Email | GitHub Username
sm | Shuyu | Meng | smeng5@stevens.edu | AllisonMSY
fz | Fangzhou | Zhang | fzhang23@stevens.edu | zfz
hy | Haolin | Yang | hyang40@stevens.edu | TyrangYang
zh | Zeyu | Huang | zhuang47@stevens.edu | zeyuhzh135
|  |  | GitHub Repository: | ssw555-tm02-2019Fall

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Dates before current date | sm | Done
1 | US02 | Birth before marriage | sm | Done
1 | US03 | Birth before death | fz | Done
1 | US04 | Marriage before divorce | fz | Done
1 | US05 | Marriage before death | hy | Done
1 | US06 | Divorce before death | hy | Done
1 | US07 | Less then 150 years old | zh | Done
1 | US08 | Birth before marriage of parents | zh | Done
2 | US09 | Birth before death of parents | sm | Done
2 | US22 | Unique IDs | sm | Done
2 | US23 | Unique name and birth date | fz | Done
2 | US24 | Unique families by spouses | fz | Done
2 | US10 | Marriage after 14 | zh | Done
2 | US25 | Unique first names in families | zh | Done
2 | USC01 | Trace error line | hy | Done
2 | USC02 | Get rid off the invalid income | hy | Done
3 | US21 | Correct gender for role | sm | Undo
3 | US15 | Fewer than 15 siblings | sm | Undo
3 | US35 | List recent births | fz | Undo
3 | US36 | List recent deaths | fz | Undo
3 | US30 | List living married | zh | Undo
3 | US31 | List living single | zh | Undo
3 | US39 | List upcoming anniversaries | hy | Undo
3 | US38 | List upcoming birthdays | hy | Undo

## Burndown README
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2019-09-25 | 32 |  | 0 | 0 | 0
Sprint 1 | 2019-10-09 | 24 | 8 | 460 | 200 | 138
Sprint 2 | 2019-10-20 | 16 | 8 | 712 | 270 | 56
Sprint 3 | 2019-11-06 | 8 | 8
Sprint 4 | 2019-11-20 | 0 | 8

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2019-09-25 | 32 | 0 | 0 | 0 | 0
2019-10-09 | 24 | 8 | 460 | 200 | 138
2019-10-20 | 16 | 8 | 712 | 270 | 56

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Story Point | Completed
US01 | Dates before current date | sm | Done | 15 | 25 | 46 | 30 | 5 | 10/8/2019
US02 | Birth before marriage | sm | Done | 20 | 30 | 18 | 20 | 5 | 10/8/2019
US03 | Birth before death | fz | Done | 20 | 30 | 13 | 15 | 5 | 10/8/2019
US04 | Marriage before divorce | fz | Done | 20 | 30 | 16 | 15 | 5 | 10/8/2019
US05 | Marriage before death | hy | Done | 20 | 30 | 20 | 25 | 5 | 10/8/2019
US06 | Divorce before death | hy | Done | 20 | 30 | 21 | 35 | 5 | 10/8/2019
US07 | Less then 150 years old | zh | Done | 10 | 20 | 21 | 30 | 5 | 10/8/2019
US08 | Birth before marriage of parents | zh | Done | 25 | 40 | 26 | 30 | 5 | 10/8/2019
Review Results:
Generally, the code works for all the stories we implemented in this story. However, there still exists some shortage of the code. We need to improve the performance of the reading method and the line number of the error in gedcom file should be trackeded. Thus, we plan to implement the new read function which can trace the line number in next sprint.
Keep doing:
Efficient and effective team communication
Writing test case first
Using Travis CI
Avoid:
Less group working time
Different coding style

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Story Point | Completed
US09 | Birth before death of parents | sm | Done | 25 | 30 | 42 | 40 | 5 | 10/20/2019
US22 | Unique IDs | sm | Done | 30 | 30 | 30 | 30 | 5 | 10/20/2019
US23 | Unique name and birth date | fz | Done | 30 | 30 | 15 | 30 | 5 | 10/20/2019
US24 | Unique families by spouses | fz | Done | 30 | 30 | 16 | 30 | 5 | 10/20/2019
US10 | Marriage after 14 | zh | Done | 25 | 30 | 20 | 20 | 5 | 10/20/2019
US25 | Unique first names in families | zh | Done | 30 | 30 | 29 | 30 | 5 | 10/20/2019
USC01 | Trace error line | hy | Done | 200 | 120 | 60 | 40 | 13 | 10/20/2019
USC02 | Get rid off the invalid income | hy | Done | 50 | 60 | 40 | 50 | 8 | 10/20/2019
Review Results:
In this sprint, we have implemented all eight stories as we planned. Now, the program will report the error for the person whose birth is after parents' death, the duplicate IDs, the duplicate name and birthday, the person whose marriage is before 14, the duplicate first names in a single family and check the spouses has a unique family. The code now can trace the line number and get rid off the invalid incomes while reading the gedcom file. The user story USC01 has similar functionality as US40. However, we do refactoring the object constructor attributes and variables to achieve a better perofomance of reading method.
Keep doing:
Refactoring the code to eliminate bad smells. Efficient and effective team communication.
Avoid:
When we implemented some stories, some additional functions which should be retreated as exclusive stories had been added. We need to better plan our stories to avoid achieving extra stories in a single story implement.

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US21 | Correct gender for role | sm | Undo | 20 | 30
US15 | Fewer than 15 siblings | sm | Undo | 20 | 30
US35 | List recent births | fz | Undo | 20 | 30
US36 | List recent deaths | fz | Undo | 20 | 30
US30 | List living married | zh | Undo | 20 | 30
US31 | List living single | zh | Undo | 20 | 30
US39 | List upcoming anniversaries | hy | Undo | 20 | 30
US38 | List upcoming birthdays | hy | Undo | 20 | 30

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique family by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)
USC01 | Trace error line | The line number should be tracked while reading gedcom file in order to figure out the error line number
USC02 | Get rid off the invalid income | In order to accept redundant lines in gedcom file, the read method should get rid off the invalid lines.